## EFFORT
| Iteration 1 4 wks |  | Iteration 2 4 wks |  | Iteration 3 4 wks |  | Total |  | Dependencies
| 2018-03-19 | 2018-04-15 | 2018-04-16 | 2018-05-13 | 2018-05-14 | 2018-06-11 |  |  | Use Case | Desc | Actor | System | Depd | Priority | Points
pts/it (3/w) | 12 |  | 12 |  | 12 |  | 36 |  | UC01 | Search for Programs | Web User | SAMS | None |  | 1
hours of effort | 480 |  | 480 |  | 480 |  | 1440 |  | UC02 | Display Program Detail | Web User | SAMS | UC01 |  | 0.4
|  | 135 |  | 85 |  |  |  |  | UC03 | Submit Online Application | Student | SAMS | UC04 |  | 4
| UC05 | 2.5 | UC09 | 85 |  |  |  |  | UC04 | Login | Student | SAMS | None |  | 2.4
| UC08 | 2.5 | [6 empty] | UC05 | Logout | Student | SAMS | UC04 |  | 0.2
| UC02 | 5 | [6 empty] | UC06 | Edit Online Application | Student | SAMS | UC03 |  | 1.5
| UC07 | 7.5 | [6 empty] | UC07 | Check Application Status | Student | SAMS | UC03 |  | 0.6
| UC01 | 12.5 | [6 empty] | UC08 | Submit Recommendation | Faculty | SAMS | UC03 |  | 0.2
| UC06 | 20 | [6 empty] | UC09 | Approve Course Equivalency Form | Advisor | SAMS | UC03 |  | 6.4
| UC04 | 32.5 | [12 empty] | 16.7
| UC03 | 52.5
Base upon the Agile Effort estimation that I performed, I found that the project could be completed in less that 3 one month iterations. Originally, I had started the Fibonacci Series at .5 up to 34 hour. Even adding 2 hours only extended the project to 6 weeks or approcimately 1 1/2 iterations.
|  | Risk |  |  | Risk Resolution Measures |  |  | Justification
| 1 | Real time performance shortfalls |  |  | add hours to the estimated effort |  |  | Probably a gross underestimation on my part. And realistically I would not be able complete the work in that short of a time period.
| 2 | Unrealistic Schedule and Budget |  |  | adding hours to the Estimated Effort will increase the completion timeline |  |  | Increasing the completion and milestones timeline will decrease the amount of stress and pressure on the team.
| 3 | Developing the Wrong Function and properties |  |  | Taking and reusing written codes and functions such as login, logout, form submissions and notifications. |  |  | Using functioning codes and separating methods and functions meets the design for change criteria.
| 4 | Developing the Wrong user interface |  |  | There are 4 different users: web user (non registered), student (registered), faculty (registered), advisor (registered) |  |  | Ensuring the correct users have access to the information and interfaces they need. For example, the student should have an application status and be able to edit unsubmitted applications.
| 5 | Continuing Stream of requirements changes |  |  | Use GITHUB to get change proposal and buyin from the whole team. |  |  | A continuing stream of requirements changes can be difficult to track and understanding the purpose of the changes, whether it is necessary or not.

## RISK
| Risk | Risk Resolution Measures | Justification
1 | Real time performance shortfalls | add hours to the estimated effort | Probably a gross underestimation on my part. And realistically I would not be able complete the work in that short of a time period.
2 | Unrealistic Schedule and Budget | adding hours to the Estimated Effort will increase the completion timeline | Increasing the completion and milestones timeline will decrease the amount of stress and pressure on the team.
3 | Developing the Wrong Function and properties | Taking and reusing written codes and functions such as login, logout, form submissions and notifications. | Using functioning codes and separating methods and functions meets the design for change criteria.
4 | Developing the Wrong user interface | There are 4 different users: web user (non registered), student (registered), faculty (registered), advisor (registered) | Ensuring the correct users have access to the information and interfaces they need. For example, the student should have an application status and be able to edit unsubmitted applications.
5 | Continuing Stream of requirements changes | Use GITHUB to get change proposal and buyin from the whole team. | A continuing stream of requirements changes can be difficult to track and understanding the purpose of the changes, whether it is necessary or not.